## RAM
Project RAM Detail
Project Name: | MMG Network Design
Project Manager: | Andrea Wager
Stakeholders
WBS Activities | Andrea Wager | Sherri Smith | Mike Batiz | Jason Skinner | Fred Brown | Ted Emigh | Kevin Paulus | MMG
| Project Manager | Financial/ Legal Mgr. | Technical Architect | Project Leader | Risk/Disaster Manager | Applications Developer | PM Consultant | Sponsers
Initiation (Concept Phase)
Project Request | AS | AS | - | - | - | - | R | A
Define Mission, Objectives, Deliverables | bar: AS to A
Project Organization | AP | P | P | IP | P | P | P
Cost Estimate | S | AS | I | PI | - | I | - | -
Risk Assessment | PS | - | - | - | A | - | - | -
Develop Project Charter | S | A | - | R | - | - | R | -
Planning Phase
RFP Development | AS | S | P | S | P | P | R | -
Vendor Selection | - | - | P | AS | P | P | - | -
Scope Statement | S | A | - | - | - | - | R | S
WBS | S | AP | P | P | P | P | R | -
Project Schedule | AS | P | P | P | P | P | R | I
Communications Plan | A | P | P | P | P | P | R | -
Project Budget | AR | A | - | - | - | - | R | S
Quality Plan | AS | P | P | IPS | P | P | R | -
CAD Architecture | IR | - | - | AIPS | - | - | R | R
Network Design | A | P | P | IP | P | P | R | R
Test Plan Phase
Hardware | R | - | I | AS | I | I | - | -
Software | R | - | I | AS | A | A | - | -
Cableing | R | - | I | AS | I | I | - | -
Construction (Execution Phase)
Product Development | APRIS | API | API | API | API | API | R | -
Quality Control | RS | - | P | APIS | P | P | R | -
Quality Assurance | ARS | P | P | P | P | P | R | -
Documentation | RS | A | - | - | - | - | R | S
Training Development | RS | - | P | AS | P | P | R | IP
Configuration Management | RS | - | A | PRS | A | A | R | P
Testing / Rollout Phase
System Testing | RS | - | A | PRS | A | A | - | IP
Rollout | AS | P | P | P | P | P | R | IP
Project Close | AS | SP | P | P | P | P | R | S

## Definitions
DEFINITIONS
CODE
A | Accountable | Responsible for success/failure of this activity.
P | Participant | Actively participates in this activity.
R | Review Required | This person must review the output of this activity.
I | Input Required | Project Team needs input from this person in this activity.
S | Sign-off Required | Must sign-off the appropriate document.