## Sheet1
Categories | Status | Assignee | Office Name | Reported by | Questions or concerns | Update
EMR | Complete | Edy Navalo | Thomas Peds | Jennifer Elkins | Order folder reconfiguration | 1/9 - Completed and messaged to Jennifer
EMR | Complete | Kaye Crowther | Thomas Peds | Jennifer Elkins | Add 90461 CPT Code | 1/10 - Dana/Melissa reached out. ok with order folder reconfig. No careset changes at this time - Thomas Peds Notified.
EMR | Complete | Kaye Crowther | Stanley/ Fountain | Kim Waters | semen analysis- can order be undone (the nurse put in accidently) | 1/11/13 Kaye reached out to Kim with instructions.
EMR | Complete | Kaye Crowther | Stanley/ Fountain | Kim Waters | order build request x 2 (1/14/13) order careset build x 2 (1/11/13), order folder reconfiguration | Completed Change - Office Notified.
Training | Complete | Melissa Gomez | Lake County Group | Lake County Group | What can be done to change an order added to the wrong patients chart | 1/9/13 - It was messaged to the group that they would need to Cancel/DC the orders that were entered on the wrong pts. Chart.
Operations | Complete | FHMG Operations | Lake County Group | Lake County Group | it was identified that some Offices are still using superbill instead of entering charges in the system 1/23/13 Correction: per Lisa they are using it with entering charges into Cerner | 1/15/13 - Email sent to Amy and Randall for awareness. Informed Melissa many OM's spoke to this.
Operations/EMR | Complete | Amy Schnebel/Freddy Altemose | Lake County Group | Lake County Group | Meaningful Use Scorecards- When do Providers get added and who will be sending it to them. | 1/10/13 Providers are getting added as they go live. The MU dashboards will be posted on a secured drive and be made available for the Directors to retrieve on a weekly basis. As a reminder Office Managers and Directors have the ability to run the detailed reports for MU.
Operations | Complete | David Middag | Lake County Group | Lake County Group | Better system to add codes, when requested. David mittag- emailed Kim Travis to approve prior to content build | 1/9/13 Per our meeting, David Middag would be following up with operations.
Reg/Sched | Complete | Robin Rebusman | Lake County Group | Lake County Group | Flag bad debt patients for registration. Is their a possibility to do that with in cerner | 1/16/13 Education sent by Robin to Laura, Michelle, Nancy
EMR | Complete | Jackie Icaza | Dr. Tulley's Office | Virginia | Dr. Tulley- not able to view messages in his inbox | 1/10/13 per Jackie I spoke with Virginia the office manager. She confirmed that Dr. Tulley was not having any issues with message center right now. I was not able to determine what actually happened. He does have multiple sessions open at one time which may have contributed to the issue.
EMR | In Progress | Lloyd Opina | ` | Tiffany Westbrook | Freezing and locking | 1/14/13 - Per Smart Auditor, user is performing Depart function on multiple users at once. This is known to cause the "Insuffiencient Memory" and Freezing. Office has been notified. 1/28/13 Per Lisa issue of having the computers freezing and locking up several times a day is still continuing , even though we are not having multiple computers up for the depart process. So, I would keep this issue open and not closed. We have made an earnest attempt to make sure that that multiple encounters are not up at the same time, and we are still getting the freezing. John, the tech that usually comes out, has indicated that MIS is still not sure why this is happening. It would be good if we could get an answer to the issue, as it has been going on for several months. 1/28 Lloyd will follow up with the Office
EMR | In Progress | Lloyd Opina | Lake Primary Care Assoc. - Martello | Sheri Hardwood | Freezing and locking | 1/28/13 Per Lisa issue of having the computers freezing and locking up several times a day is still continuing , even though we are not having multiple computers up for the depart process. So, I would keep this issue open and not closed. We have made an earnest attempt to make sure that that multiple encounters are not up at the same time, and we are still getting the freezing. John, the tech that usually comes out, has indicated that MIS is still not sure why this is happening. It would be good if we could get an answer to the issue, as it has been going on for several months. 1/28 Lloyd will follow up with the Office
EMR | In Progress | Lloyd Opina | Dr. Eagle's Office | Jamie Osborne | Freezing and locking | 1/28/13 Per Jamie Osborne: Dr. Eagle’s office is also one that freezes up or just goes down
Hardware | Complete | Robyn Lloyd | Lake County Group | Tiffany Westbrook | Need to work the Number to times you have to log into system Providers requested Tap and Go. | 12/9/13- Tap and Go implemented as a pilot for Dr. Vue and Dr. Boggus. Further discussion being had with FHMG Leadership for funding 1/23 Device team working closely with the office during this pilot phase of tap and go.
EMR | Complete | Freddy Altemose | Lake County Group | Tiffany Westbrook | Work on number of times you have to refresh in the system | 1/15/13 System is set to refresh in some windows automatically Since mulitple users contribute information for patients concurrently it is best practice to hit the Refresh button so that you can work with the most up to date informaiton for the selected patient. 1/28/13 Freddy to reach out to Tiffany on current functionality.
EMR | Complete | Training | Lake County Group | Tiffany Westbrook | Where can we list patients specialist in Chart | 1/9/13 Currently it is trained to enter that information into the problem list as a free text so tht the provider can see in the Ambulatory Summary view.
EMR | Complete | Jackie Icaza | Lake County Group | Tiffany Westbrook | Add 3 week follow up as a choice in the follow up screen | 1/23/13 Approved by the committee. Will be added in the next week. Jackie reached out to Tiffany to provide an update update.
Training | Complete | Mary Moore | Colon and Rectal Group |  | Favorites Folder "Disappears" | 1/23/13 educate to ensure on correct encounter.
EMR | Complete | Evan Farnsworth | Colon and Rectal Group |  | Ability to "Cross Out" negative findings for all entries in powernote. Works for some fields and not others | 1/23/13 complete
Training | Complete | Mary Moore | Colon and Rectal Group |  | Favorites Folder a. Ablility to use and "see other Provider Favorite b. Ability to move things out of the Favorite Folders or create new folders | 1/23/13 complete
EMR | Complete | Edy Navalo | Colon and Rectal Group |  | Surgery Scheduling Order, only able to put in 25 characters | 1/23/13 Per Edy they have increased the characters to 80 and are exploring the option to have it increased further. Informed Dr. Attallah. Created ticket to increase to 20, will inform the office when complete. Working with the discern team.
Training | Complete | Mary Moore | Colon and Rectal Group |  | Inablilty to "Deselect" a powerplan once it's been selected | 1/23/13 Training was provided to the Doctor. We will make sure to reinforce this in provider training
Training | Complete | Mary Moore | Colon and Rectal Group |  | THE PRINTED NOTE DOES NOT FLOW PROPERLY , ESPECIALLY WITH REGARD TO THE ASSESSMENT AND PLAN. The way it comes out has information that the clinical provider and consultants aren’t looking for (example: in a plan – “Discussion with patient / caregiver: Adequate fiber and hydration” when really the plan is “Let’s get a gastrograffin enema to test the anastomosis - to see if this patient’s ileostomy can be closed” | 1/14/13 Utilize Consult Letter
Training | Complete | Mary Moore | Colon and Rectal Group |  | Can a Diagnosis be automatically populated into the Diagnosis part of the Powerchart | 1/23/13 Dr. Attallah was trained on this.
Training | Complete | Mary Moore | Colon and Rectal Group |  | Can Powerplan be set to default where it automatically brings up the Powernote (without having to select "Colorectal Surgery Office Note FHMG" from Window | 1/23/13 Not a cerner functionality.
EMR | Waiting on Customer | Kaye Crowther | Dr. Eagle's Office | Lake County Group | Dr. Eagle- ePrescribing routing issues | 1/11/13 kaye: Spoke to Tesa one of the nurses at the office. She reports some prescriptions are not getting to the pharmacies per their patients. It happens to both Dr. Eagle and Cynthia (the ARNP). Validated with Cerner their SPI numbers are active and also both Providers did NOT receive any routing errors week of 1/11/13. I asked Tesa if she could start providing me patient name, drug and pharmacy examples so I can research. She said she would let Jamie know too… 12/3/12 Kaye reached out to the OM for the same reported issue. never responded in order to investigate failures.
EMR | Waiting on Customer | Troy Reasoner | Dr. Eagle's Office | Lake County Group | Labs results not posting into Cerner for FHL | 1/11/13 - Researched FHL accounts for Dr. Eagle's office and noted that all Lab orders were received at FHL. Troy reached out to the Office Manager,Jamie Osbourne to receive an Account example to further troubleshoot. 1/28/13 Freddy reached out to the OM, is aware of why this issue is happening(paper req’s). told both office managers that we are working with Quest to resolve these errors.
EMR | Waiting on Customer | Troy Reasoner | Dr. Wagner's Office |  | Labs results not posting into Cerner for FHL | 1/15/13 reached out to the Office regarding Dr. Wagners results. Asked for specific results not posting. Research showed, endorsed results, patients hadn't gone to the lab yet 1/28/13 Freddy reached out to the OM, is aware of why this issue is happening(paper req’s). told both office managers that we are working with Quest to resolve these errors.
Operations | In Progress |  | Lake County Group | Lake County Group | Randall's biller not able to access scanned images to retrieve ins cards. Can biller be granted access so that they can pull their own information. | 1/15/13 - Email sent to Amy and Randall for further review. 1/23/13 Melissa Lead Trainer to test postion, working with Randall. 1/23 request to be changed to the billing position. for testing, Randall involved.
Reg/Sched | In Progress | Mark Morrison |  | Michelle McWilliams | Registration dropping insurance information and not carrying order to mysis a. Priority is wrong b. Losing ssn c. Losing referral information d. losing Eligibility date e. Marital Status not holding | 1/10/13 - Marital Status not sticking is a known issue, currently there is an open SR. Reg/sched team reached out to Michelle McWilliams to provide examples for further troubleshooting on the reported concerns. Reg/sched will continue to to work with Cerner and provide updates as they become available.
Operations |  | Melissa Martinez/Gomez |  |  | Charges/credits what is the process when credit it in mysis. What to do in cerner | 1/15/13 - Emailed for training points on this.
EMR Project Team | In Progress | EMR Project Team |  |  | Create process who/when/where. i.e. reg/sched, support center | 1/10/13 Identifying all the avenues in which request are coming in aswell as the point person for each area
EMR | Following up |  |  |  | Cypress inbox- could all results go via cypress instead of faxing. | 1/10/13 Following up with various teams to investigate content in Cypress.
System Performance | Complete | Lloyd Opina | Colon and Rectal Group |  | Error messages and Freezing of Clock | 1/10/13 Analysis for revealed no freezing/errors. OM updated, will report occurances shall they occur again for us to investigate.
Operations |  |  |  |  | Dictation available in Clinic - a. This is mandatory in the hospital within 24 hours b. as Hospital Employees, can we not develop a way to dictate office visits through the existing hosptial Dictation System | 1/13/13 Operations
Radnet team | In Progress |  |  |  | Patient had wrong study due to EMR "Override" of Verbatim Order. | 1/13 following up with Nisha and Jared from the Radnet Team. 1/23/13 Radnet training issue. reached out to the team to follow up with the Rad dept in the hosp/Fri.
Operations | In Progress |  |  |  | Monitors in Exam room are not being used by Physician or MA. Is there a better place for them. | 1/23/13 operational decision to hold off moving hardware until mid year review
EMR | In Progress |  |  |  | Barrum Enema ways to Administer Order. | 1/23/13 discussion whether a new order for gastrografin enema and for gastrografin swallow need to be added to the catalog. Radiology is following up.
Operations | In Progress |  |  |  | Can Tap and Go be installed | 1/23/13 This is currently being Reviewed for approval by Senior Leadership.
Training | Following up |  |  |  | Assessment and Plan: again, auto-populating the note would work best, but this area is quite jumbled together. Spacing out, color coding, and perhaps increasing the font size are little things that can help us sort through this quicker with less frustration | 1/23 per Dr. Meyer increase the font 1/28/13 f/u email to mary for validation of f/u
EMR | In Progress |  |  |  | a. At this point, the power note starts to become repetitive and confusing: | 1/23/13 will need approval from the colo rectal group prior to change, meeting scheduled 1/31/13 per Kim
EMR | In Progress |  |  |  | Can the main template for a note be defaulted to "Show Structure" rather than having to click on that every time | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Under "Visit Information" can the note starte ith Chief Complaint? Also "Anorectal Pain" should be one category or Anal Pain and a Second for Rectal pain. These are extremely common problems. For all the other categories, "Not Applicable" should be added | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Previous Colonoscopy Has "Cross Out" which is great, but associated syptoms does not. "No Associated Symptons" is a Pertin. Negative. | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Shouldn't side menu read HPI rather than visit information. | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Need a section that says "Prior review of systems reviewed, no significant changes" or prior ROS Reviewed , changes included | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Can you color code the abdomen and colorectal exam to help "quickly find" these 2 areas when scrolling through powerchart | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | For Colorectal Procedure: Please add High Resolution Anoscopy | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Assessment and Plan : can the note be auto populated. Please space out, color code and perhaps increase the font size | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Why is there a DX nd Plan (Repeat) there is an assessment, buth then a colorectal plan, and then after that a Plan. A bit confusing | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress
EMR | In Progress |  |  |  | Printed Notes does not flow properly, especially with regart to the Assessment and plan. | 1/23/13 meeting scheduled 1/31/13 with Providers and Kim. Will update on progress 1/28/13 per dr. meyer: This is a powernote issue that we need to review in detail (Evan and me and physicians).
EMR | Cerner Enhancement Request | Freddy Altemose | Lake County Group | Tiffany Westbrook | When you type in Follow up you have to search for the Dr. to follow up with this. Should stay as an option at the bottom | 1/13/13 Enhancement Request has been placed with Cerner for this.
Operations | In Progress | FHMG Operations | Lake County Group | Tiffany Westbrook | Update on Scribe Process and when will this be available for use | 1/23/13 Item for discussion at Ops/IT