## Sheet1
TIME | TASK | ASSOCIATED DETAILS | PERSON RESPONSIBLE
SET-UP
6:00 | Stage set-up | Speakers, microphones, instruments, etc. brought and set up on stage | Georgie, Tom
6:30 | Tables and chairs arrive | Direct delivery people from Party Hosters Inc.where to put tables and chairs | Julio
6:40 | Bring needed supplies for registration desk | Tickets, cash box, sign for tabletop, pens | Penny
6:40 | Bring needed supplies for Nature Pavilion | Hot chocolate, coffee, dispensers, donuts, cookies, paper plates and cups, napkins, sign to indicate activities sign-up table, information pamplets on all activities, pens | Roger
6:40 | Bring needed supplies for nature walks | Bird seed | Penny
6:40 | Bring needed supplies for craft tables | Craft supplies - glue, construction paper, markers, sequins, feathers, pipe cleaners, etc., brown paper roll for table tops | Nancy
6:40 | Bring needed supplies for tobogganing | Crazy carpets, sign | Richie
6:40 | Bring needed supplies for story telling | Books, cushions | Jessica
6:40 | Bring needed supplies for archery lessons | Bows and arrows, targte boards | John
6:40 | Bring needed supplies for BBQ | Food - Beef hot dogs, veggie hot dogs, ketchup, mustard, relish, mayonnaise, buns, corn-on-the-cob, watermelon, chocolate chip cookies, soft drinks and water -- supplies - paper plates and cups, napkins, utensils -- ensure all food stays regrigerated until needed | Maid Marion and the Merry Men
6:40 | Bring needed supplies for face painting | Paints, brushes | Nancy
6:40 | Bring costumes | Clown costumes | Cam
6:50 | Check-in meeting |  | Everyone
7:05 | Set-up tables and chairs | Registration table in gazebo, craft tables, picnic tables and food table outside for BBQ, food table and activities sign-up table in Nature Pavillion, face painting stations | Julio, Roger, Nancy, Riley
7:05 | Set-up toboganning station at top of Nottingham Hill | Sign, crazy carpets | Richie
7:05 | Set-up archery station | Bows and arrows, target boards | John
7:20 | Set-up storytelling station | Cushions, chair for storyteller, books | Jessica
7:30 | Volunteers start arriving | Report to Julio | Julio
7:40 | Set-up registration gazebo | Tickets, cash box, sign, pens all ready to go | Penny, volunteer
7:40 | Set-up Nature Pavilion | Food table, activities sign-up table (Note: don't make coffee or hot chocolate yet) | Roger, volunteer
7:40 | Set-up craft tables | Cover with brown paper, lay out supplies | Nancy, 2 volunteer
7:40 | Set-up face painting tables | Brushes, paints, water ready to go | Cam, volunteer
8:00 | Bouncy castle arrives | Set-up outside | Julio, Tristan, Volunteer
8:00 | Pick-up food for staff and volunteer breakfast | Bagels, pastries, muffins, jam, peanut butter, butter, cream cheese | Jessica
8:30 | Check-in meeting |  | Everyone- volunteers included
8:40 | Breakfast | Provided for staff and volunteers | Everyone
9:00 | Trio arrives for sound check | On stage | Julio
9:00 | Prepare hot beverages for food table in Nature Pavillion | Coffee, hot chocolate | Roger, volunteer
9:00 | Clowns get into costume |  | Cam, 3 volunteers
9:00 | Ensure washrooms are clean | Clean and toilet paper, paper towel stocked | Riley, volunteer
EVENT
9:30 | Event starts
9:30 AM-1:30 PM | Registration gazebo | Guests purchase tickets and are directed to Nature Pavilion | Penny, volunteer
9:30 AM-2:00 PM | Refreshments and activities sign-up in Nature Pavilion | Guests enjoy refreshments and can look through activity pamphlets and sign-up for some if interested | Roger, 2 volunteers
9:30 AM-1:30 PM | Craft tables open |  | Nancy, 3 volunteers
9:30 AM-1:30 PM | Face painting tables open |  | Riley, volunteer
9:30 AM-2:00 PM | Trio on stage | Play throughout the day | Georgie, band
21:40 | Cue Sheriff | Bring to stage for opening speech | Tom
9:45 | Welcome speech from the Sheriff of Nottingham | On stage | Tom, Sheriff
10:00 AM-10:30 AM | Archery lessons |  | John
10:00 AM-10:30 AM | Storytelling in the Pavilion |  | Jessica
10:00 AM-11:00 AM | Tracking Animals with Robin Hood |  | Julio
10:15 AM-11:15 AM | Friar Tuck's Bird Watching Tour |  | Tristan
10:30 | Begin setting up BBQ area | Get food from fridge, set-up BBQ | Maid Marion and the Merry Men
10:30 AM-1:30 PM | Toboganning | On Nottingham Hill | Richie
11:00 AM-11:30 AM | Archery lessons |  | John
11:30 AM-1:30 PM | BBQ | Food available for guests | Maid Marion and the Merry Men
11:30 AM-12:00 PM | Storytelling in the Pavilion |  | Jessica
12:00 PM-1:00 PM | Tracking Animals with Robin Hood |  | Julio
12:15 PM-1:15 PM | Friar Tuck's Bird Watching Tour |  | Tristan
1:00 PM-1:30 PM | Archery lessons |  | John
13:25 | Cue King John | Bring to stage for closing remarks | Tom
13:30 | Begin closing down all activities |  | Everyone
13:30 | Closing remarks - King John | On stage | Tom, King John
14:00 | Event over | Guests leave
TAKE DOWN
14:20 | Check-in meeting |  | Everyone
14:30 | Take down and clean registration gazebo | Make sure cash goes is counted, table is taken down and area is clean | Penny, volunteer
14:30 | Take down and clean Nature Pavilion | Put all food away, clean drink dispensers, tables taken down and area clean | Roger, 2 volunteers
14:30 | Take down and clean craft areas | All craft supplies cleaned up and put away, tables taken down, chairs stacked, area cleaned | Nancy, 3 volunteers
14:30 | Take down and clean storytelling area | Cushions collected, any chairs stacked, area cleaned | Jessica
14:30 | BBQ and picnic area taken down and cleaned | Picnic tables wiped down, BBQ put away, all food put away, any garbage picked up, area cleaned | Maid Marion and the Merry Men
14:30 | Take down toboganning area | Crazy carpets collected, area cleaned | Richie
14:30 | Take down and clean archery area | Bows and arrows, target boards collected, area cleaned | John
14:30 | Take down and clean stage | All microphones, speakers, cords, etc. taken down, put away, area cleaned | Georgie, Tom
14:30 | Take down bouncy castle | Deflate, pack up, clean area | Tristan, Volunteer
15:00 | All tables and chairs collected | Make sure all tables and chairs are collected and ready to go | Julio, volunteer
15:30 | Table and chair pick-up | Make sure people from Party Hosters Inc. are given all the tables and chairs | Julio
15:40 | Bring back bouncy castle to rental store |  | Tristan
16:00 | All areas should be cleaned up |  | Everyone
16:05 | Check-in meeting and thanks |  | Everyone
16:15 | Staff and volunteers free to leave |  | Everyone