## Sheet1
Drury University Efficiant Communicators
Efficiantly communicating with Drury students through the most efficiant communication portal
Task | Details | Sept. | Sept. | Sept. | Sept | Oct. | Oct. | Oct. | Oct. | Oct. | Nov. | Nov.
|  | 2--8 | 9--15 | 16--22 | 23--29 | 30--6 | 7--13 | 14--20 | 21--27 | 28--3 | 4--9 | 11--16
|  | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3
Overview
Background Research | Read 10 peer reviewed articles | bar: Week1 to Week2
and type 10 fact sheets
concerning communication techniques
and methods
Meeting | Meet with Mark Miller and Jann | bar: Week3
Holland to do backround research
on previous methods that were
previously used to communicate with the
Drury Community
Certification | Apply and Receive IRB approval, Mary Utley | bar: Week3 to Week4
Interviews | Interview 20, Drury Students, find out their ideas | bar: Week1 to Week3
and concerns with the current communication
systems
Interviews | Interview 15 student focus group and learn their | bar: Week2 to Week4
feelings towards the trial methods and how they
would feel it was implemented
Meeting | Meet with Mark and Jann and share new | bar: Week4 to Week1; Week4
information and seek any recommendations
they may have.
Research & Ideas | Investigate potential methods to inform | bar: Week4 to Week4
students on communication
Compliation | Compile all found information and | bar: Week4 to Week2
analayze data and make recommendations for
the Marketing & Communication Department
to follow to enable a more proficient
means to communicate with students